- General Information

| Project Title: | YFN LITERACY – Follow-up to the YFN Literacy Framework Development Workshop hosted in January 2014 and to work connecting the Yukon Literacy Strategy to the Framework. |
| --- | --- |
| Brief Project Description: | This project involves working with FNEC and individual YFNs to develop an overall framework that is representative of YFN Literacy, which will be a living document based on individual YFN Literacy Plans. The project will also support YFNs that wish to develop community based Literacy Plans. A pilot project will be designed, implemented and evaluated to provide a model process for the design, development, implementation and evaluation of a local literacy initiative from curriculum to delivery to assessment. The project will be under the advice and guidance of a YFN Literacy Sub-committee, whom will report to the FNEC. |
| Prepared By: | Tina Jules, Education Director, CYFN; FNEC Member |
| Date: | May 16, 2014 | Version: | 1.0 |

- Project Summary

GOAL & The overall project goal is to work towards closing the gap by improving YFN student learning outcomes in literacy. OBJECTIVES: To contribute to improving literacy rates; To increase the number of literacy programs and initiatives that have embedded YFN literacy priorities and perspectives; and To support YFNs in developing, implementing and evaluating local literacy programs that are representative of their local priorities, needs and goals. RATIONALE: Literacy, from western and traditional perspectives are positively correlated to success in life: higher income levels; higher education levels, sense of belonging, strong identity, etc. YFN Literacy Rates in English are in dire need of increasing – across the spectrum of lifelong learners YFN Literacy Rates as it relates to traditional perspectives will need to be incorporated into educational programs, curricula, assessment, data, reporting, etc. STRATEGIES: Identify YFN philosophies, definitions, goals and outcomes for ‘literacy’ from a traditional perspective Identify the First Nation cultural perspectives, ways of knowing and doing that will support excellence in English – reading, writing, speaking, understanding (and other areas) First Nation Pilot Project – Designing, Implementing & Evaluating a FN Literacy Program and embedding traditional FN priorities and perspectives into English Literacy Development programs To work with stakeholders in Yukon literacy to embed YFN literacy priorities and perspectives To learn from the Pilot Project and roll out initiative with participating YFNs. To closely monitor and evaluate this project on an annual basis. OUTCOMES: A YFN Literacy Framework will be produced with on-going implementation strategy Support YFNs to produce local First Nation Literacy Plans FN Literacy Pilot Project implemented and evaluated YFN perspectives incorporated within Yukon Literacy Strategy and Action Plan Evaluation system in place that produces progress on YFN literacy based on qualitative and quantitative data, which will be incorporated into the YFN Student Success Reports.

#### Project Scope

There are 14 Yukon First Nations with 8 different language groups and all nations use the English language as well. First Nations have indicated that the definition of literacy from a First Nation perspective encompasses language, land, animals, laws, values and practices – reflecting the past, present and the future. This project encompasses all Yukon First Nations that express interest in participating. The pilot project will involve one First Nation. The Sub-Committee composition will be confirmed by FNEC.

#### Project Milestones

.

| Milestones | Deliverables | Date |
| --- | --- | --- |
| YFN Literacy Framework Development Workshop | Draft YFN Literacy Plans - Outlines Draft YFN Literacy Framework | Jan 2014 |
| FNEC Endorsement of YFN Literacy Report and Implementation Strategy | FNEC support for Imp Plan/Strategy | May 2014 |
| Establish Sub-Committee for YFN Literacy (consider partners and stakeholders) | Sub-Committee established Further Develop YFN Literacy Framework Advice and Direction for Pilot Project Develop Implementation Plan | June 2014 |
| Secure Funding and Resources | Proposal to Advanced Education, PSB, AANDC and perhaps CDF or other agencies | Aug 2014 |
| Design, Implement & Evaluate Pilot Project | Pilot Project Implemented & Progress Report | Sept-Mar 2015 |
| Community Consultations to further develop YFN Literacy Plans | Participating First Nations have community based Literacy Plan | Sept-Mar 2015 |
| Further development of YFN Literacy Framework | On-going embedding individual FN Plans within the overall YFN Literacy Framework | Sept-Mar 2015 |
| On-going Progress Reports to FNEC | YFN Literacy Updates at FNEC Meetings | On-going |

- Impact Statement

- Literacy - language and culture (one’s personal identity) is positively correlated to self-confidence, pride and achievement of potential in school, at work and in life. Personal identity is related to building a foundation that personal achievements and success rests upon.

- Literacy is positively connected to achievement in school, at work and in life.

- Higher employment rates connected to literacy achievement.

- Higher employment rates lead to self-reliance and self-sufficiency.

.

| Potential Impact | Systems / Units Impacted |
| --- | --- |
| Positive impact upon all YFN languages | All participating Yukon First Nations |
| Positive impact upon literacy outcomes for YFNs as it pertains to the English language | Yukon Education, Early Learning Organizations, Literacy Stakeholders |

- Resources

| Resource | Constraints |
| --- | --- |
| YFN Literacy Coordinator | Submitted small proposal to get the initiative started, however waiting for confirmation of Funding Approved |
| Travel to Communities | Will require additional proposal submissions. |
| Meetings with Stakeholders & Partners |  |
| Sub-Committee |  |
| Program Materials and Supplies |  |
| Telephone, Fax, Internet |  |
| Printing, Photocopying |  |
| EXPENSE | DESCRIPTION | ANNUAL BUDGET |
| 6616 | Administration | $ 2,280.00 |
| 6620 | Employee Travel | $ 3,000.00 |
| 6724 | Elder/Mentoring/Cultural Services | $ 2,500.00 |
| 6633 | Other - Costs for Community Consultations on Pilot | $ 1,000.00 |
| 6612 | Professional Services/Consulting Fees | $ 15,000.00 |
| 6650 | Materials and Supplies | $ 300.00 |
| 6663 | Printing or Publishing Costs | $ 1,000.00 |
|  | TOTAL | $ 25,080.00 |

- Project Risks

Identify the high-level project risks and the strategies to mitigate them.

| Risk | Mitigation Strategy |
| --- | --- |
| Being inclusive to Literacy Stakeholders & Partners | Consider stakeholders when establishing sub-committee as project will rely on effective partnerships and working with stakeholders. |
| Limited literacy funding | Consider Management Board Submission with Advanced Education, Yukon Education and funding proposal through Labor Market Framework for new position. |

- Success Measurements

Identify metric and target you are trying to achieve as a result of this project.  For example, overall cost savings of $50K or reduce processing time by 25 percent.

Pilot project design, implementation and evaluation results YFN community based Literacy Plans YFN Literacy framework Working with Department of Education and others i.e. Yukon College, to produce longitudinal data as it regards literacy rates and outcomes pertaining to YFN people. *The measurement of achievement of traditional priorities such as culture and language fluency will be over time and the assessment system will take time to develop. Curricula with goals and outcomes at progressive levels is normally in place so as to provide a framework for assessment milestones.