## Sheet1
JEAP Implementation Year 1 Update
Priority Area | Action | Year | Lead | Status
1.1 Culturally Inclusive Councils, Staff & Students | Immediate:
Establish YFN mandatory cultural awareness opportunities for all educators (that interact with the school community including school councils and Yukon Education) that are designed and delivered by YFN people. | 1. Invitation to Yukon College to share a discussion / partner on the following initiatives: | 1 | All parties
| a) Conduct an inventory of cultural awareness courses | 1 | Yukon Education / Yukon College/ FN Heritage Branch (YG)
| b) Yukon College generic on-line cultural training course | 1 | Yukon College | Done
| e) Identify issues and strategize ways to address YFN student upgrading issues | 1-2 | Yukon Education / FNEC / Yukon College
| f) Yukon College/CYFN to complete 4 individual YFN cultural training modules | 1 | CYFN / Yukon College | Yk College is working with 6 YFN cultural training modules - TTC KFN, VG, Kaska, NND and maybe CTFN. They are doing 6 instead of 4.
| 2. Yukon Education to implement a condition of hire to take the on-line FN 101 course | 1-2 | Yukon College / Yukon Education / YFNs | In Progress.
| 3. Yukon Education will work with YTA to implement the cultural awareness training for existing staff | 1-2 | Yukon Education / YFNs / FNEC
| 6. Develop and implement an in-person mandatory awareness training on IRS for Yukon Education staff and School Councils | 2 | Health and Education Commissions/ Yukon Education
1.1 Culturally Inclusive Schools | Immediate: |  | Yukon Education
To have proportionate representation of FN teachers in the school system. | 1. Perform a scan of cultural resources | 1 | Yukon Education / CYFN
| 2. Develop options and related policies for YFN local/northern hiring preferences at all levels | 1 | Yukon Education / FNEC | Dept is asking questions about how this would work.
| 3. The partners will develop a generic template for determining cultural inclusiveness of schools (to be integrated into the How Are We Doing? Report) | 1-2 | Yukon Education / FNEC | Jenn & FNEC to meet with Janet to develop a generic template for cultural inclusiveness.
1.4 K-12 Language Programs | Immediate:
To increase opportunities and supports to increase FN language fluency and rejuvenate language and cultural values | 1. Perform an inventory of YFN language programs in pre-K at FN daycares | 1 | FNEC / CYFN SGS & Health
| 2. Explore FN language rich intensive models and best practices, consolidate, compile and share out information | 1 | Yukon Education / FNEC / CYFN/ YNLC
| 3. Review YFN language programs in Yukon schools: scan of existing language teacher data, level of proficiency and depth of programming | 1 | Yukon Education
| 4. Scan of FN dictionary and language resources (books, digital) | 1 | YNLC / YFNs/ CYFN SGS/ Yukon Education
| 5. CYFN to engage with YNLC to develop a process for sharing their resources with communities | 1 | YNLC/ CYFN
| 6. Identify a pilot community, determine community readiness and local/human resources supporting a FN language immersion kindergarten program | 1 | Yukon Education / FNEC
2.1 Community Priorities | Immediate:
Establish a FN School House of Learning not limited to a building, that promotes lifelong learning and encourages a pattern of learning through YFN language, philosophy, cultural practices and knowledge-sharing | 1. Perform a scan of FN schools, models and best practices in Canada | 1 | CYFN
2.3 YFN Jurisdiction and Implementation | Immediate:
| 1. Enact the Central Indian Education Authority and Local Indian Education Authority | 1 | FNEC / Leadership
| 2. YFN School Feasibility Study | 1-2 | CYFN
| 3. Develop and implement a FNEC / CELC professional development program foundational to the establishment of a YFN School | 1-2 | CYFN
3.1 Funding, supports, resources | Immediate:
Ensure funding is in place to support the JEAP Implementation plan | 1. Dissolve the YFN EAC | 1 | FNEC / Leadership / Yukon Education | Done except for letting leadership know money has been transferred to FNEC.
| 2. Contribution Agreement with CYFN to finance/ administer FNEC for Yukon-FN Engagement (PSB and Advanced Education) | 1 | All Parties
| 3. Contribution agreements and TORs in place (Canada, Yukon – FNEC, YFNs, CYFN and subcommittees) to support actionable items and deliverables within the JEAP | 1 | All Parties | YG can show where the resources are bing spent, but can't get information about transfer $ per child and neither can the local federal office.
| 4. Define funding allocations for FN education initiatives | 1 | All Parties
| 5. Environmental scan / assessment of where we are at (through the JEAP) identifying resources, funding, programs and services already in place | 1 | All Parties
| Annual discussion on funding allocations and joint prioritizing | on- going | All Parties
3.3 Policy and Protocol Framework | Immediate:
To develop a protocol framework determining how to engage with YFNs on key issues and decisions concerning education and matters that affect YFN students. | 1. YFN Protocol Framework for engagement completed | 1 | Yukon Education / FNEC / CYFN | FNEC would like to hire a contractor to finish this work.
3.4 Accountability, Assessment and Evaluation | Immediate:
To have an annual report on YFN Education and YFN Student Achievement (How Are We Doing? Report) | 1. Data sharing agreement in place | 1 | All Parties
| 2. Meetings held to decide on what will be in the HAWD report | 1 | All Parties
School Growth Plans | 3. Develop a process to ensure FN participation in School Reviews and School Growth Plan | 1 | Yukon Government
4.1 Family, Community Engagement and Supports | Immediate:
To have parental involvement at all levels of education including parents in the classroom, volunteering, supporting learning in the home and representation on committees, School Councils etc. | 1. Develop a Community (family, community, clan) Engagement strategy | 1 | CYFN / Yukon Education
| 2. Initiate community engagement pilot projects | 1 | CYFN
4.3 Student Supports | Immediate:
To have all schools celebrate and foster cultural inclusion, provide flexible learning options and accredited language, land-based experiential learning opportunities with Elders involved in K-12 in all aspects of education. | 1. Perform a scan of FN supports in schools (Elders, tutoring etc.) | 1 | Yukon Education
| 2. Student support services, including counselling services. | 1 | Yukon Education